## Sheet1
Week # | To Do | Owned By | Deadline | Status | Comments
Week 10 - Development of Paper Prototype # 3 | Test Paper Protype 1 & 2 to new Test users | Irwin and Angelika | 2019-09-09 | Completed
| Creation of Paper Prototype # 3 | Irwin | 2019-10-09 | Completed
| Revise Needfinding | Irwin and Angelika | 2019-09-09 | Completed
Week 11 - Setting Up Digital Mockup | Start creating Digital Mockup | Angelika | 2019-12-09 | Completed
| Creation of Paper Prototype # 4 | Irwin | 2019-12-09 | Completed
| Test of Paper Prototype # 3 and # 4 to users | Irwin and Angelika | 09/15/2019 | Completed
| Implementation of interface flow in digital mockup | Irwin and Angelika | 09/15/2019 | Completed
| Make the Powerpoint presentation | Angelika | 09/16/2019 | Completed
Week 12 - Finalization of project
| Upload the testing video of new paper prototypes to youtube | Angelika | 09/16/2019 | Comlpeted
| Edit 'help' feature in prototype | Irwin | 09/16/2019 | Completed
| Add a rating feature in paper prototype | Irwin | 09/16/2019 | Completed
| Implement the edited help and rating feature on digital mockup | Angelika | 09/16/2019 | Completed
| Debug the mockup for any errors | Irwin and Angelika | 09/16/2019 | In Progress